## Sheet1
2026-05-19
| List of Items to be Updated, and Questions, for Portal | Date Requested | Priority
1 | 80/20 split for fees - can we make it either 100% when only 1 is selected - CD or CA - or take away split all together so that fees can be added at time project is put into portal | 2025-04-09 | 1a
2 | When more than one PM is listed on the project - it randomly splits the hours between them. Ex. 257101 | 2025-04-18 | Low
3 | Why does some time not show on timeline (color dot) - 241129 - Pat M - 250004 - Jeff - 243503 - JMB - 241108 - PJOD - Operator error | 2025-05-05 | Done
4 | PTO hours don't always save in portal - put PTO in and save - shows up that day and then next day its gone | 2025-06-03 | 8
5 | PTO inaccurate for: Betsy, Jacinta, Kyle, Laura, Lidiya, Nischal, Sarah L and Sarah M | 2025-06-03 | 8
6 | Nothing on timeline for hours for CEM - 252936 O.E. | 2025-07-07 | Done
7 | Searching for inactive projects - add or subtract year button - can we add a feature to be able to search multiple years? JAC suggestion - Norm will think about it, this is a speed thing. | 2025-10-31 | Low
8 | For the network search tool and reimbursables - can there be a close button instead of a cancel button? | 2025-10-31 | 2
9 | Scrolling speed needs to be slowed down - per PJOD | 2025-11-03 | 9
10 | We need a "close" button when entering data into the Employee Expense report. The only way to close the window is to click on "cancel" - per PJOD | 2025-11-03 | 2
11 | PJOD needs to walk thru adding a new employee - password set-up is not clear - need to be able to go back and add parameters. Unless every parameter is filled, it does not accept it. Make fewer entries mandatory. | 2025-11-03 | 4
12 | Moving and backing up the database - PJOD | 2025-11-03 | Done
13 | Review deleting employees and how that messes up past hours, if at all - PJOD | 2025-11-03 | Done
14 | Invoicing did not get finished - PJOD would like to review the status of everything where we stopped it | 2025-11-03 | Low
15 | Time showed up on JMB timesheet for 245061 (0.5 - 9/1-16), but was not on portal | 2025-11-05 | 11
16 | When weekend hours are added to a project, they don't always show on timesheet 255051 JMB did not - BAL did | 2025-11-05 | 11
17 | Can we have the portal add up year to date overtime? - JAC - We are electing to now do this per meeting 3/17 |  | Done
18 | When printing weekly reports - some lost the headers - project#, client#, etc. Can you check this? Didn't do it on everyone. |  | Low
19 | Possible to add a date for PTO increase or decrease - ie FWS currently working 40 hours then going to 20 hours in January so PTO will decrease | 2025-10-13 | Medium
20 | Change Project Type: "Investigation INV" to "Assessment ASM." - PJOD |  | Low
21 | Mileage rate change for 2026 to 72.5 cents - Norm will add a feature for Jen for future use. | 2026-01-07 | 3
22 | Link to Folders from the project drop down - PJOD | 2026-01-08 | Medium
23 | Can we have add service date auto-populate to current date - JMB | 2026-01-14 | 12
24 | Signatures for add service author not loading in some cases - JMB | 2026-01-14 | Medium
25 | Portal sometimes crashes when adding new employee - JMB | 2026-01-08 | Medium
26 | In the drop down for Add-Services - "from" - all PM signatures should be available - only John Brewers is currently showing as a selection - DJR | 2026-01-15 | Medium
27 | Adding new employee in portal (Abed) need timesheets to be active | 2026-01-30 | Done
28 | Refresh button does not always work - portal schedule, timesheets, etc. | 2026-02-04 | Medium
29 | Glitch creating new project folder when generating an add service - MLM | 2026-03-12 | 5
30 | Add phases to PM report | 2026-03-12 | Medium
31 | Standardize sorting of names in various locations | 2026-03-12 | Medium
32 | Can PM list be sorted by project number | 2026-03-13 | Medium
33 | Portal is lagging on Thursday when multiple users are in it. | 2026-03-16 | Medium
34 | Resolve budget calculations when pay rates change mid-project. | 2026-03-16 | 7
35 | Pat believes change password function is not working | 2026-03-16 | 6
36 | Alphabetize all lists by last name. | 2026-03-16 | 10
37 | Norm will set database to backup to Github periodically | 2026-03-16 | 1
38 | Blaise is not acruing PTO in portal | 2026-04-02